## Index
Project Name:
Soft Landings Project Log and Stakeholder List
Index | Activity | Stakeholders
Sheet 1 | Fire Management
Sheet 2 | Room Booking & Quemis
Sheet 3 | Contractors Commissioning of Mechanical & Electrical Services
Sheet 4 | Training & Demonstrations of Building Systems
Sheet 5 | Catering
Sheet 6 | O&M Manuals
Sheet 7 | IT Commissioning
Sheet 8 | Cleaning & Waste
Sheet 9 | Insurance
Sheet 10 | Rates Notification
Sheet 11 | Maintenance Contracts
Sheet 12 | Handover Documents
Sheet 13 | Security
Sheet 14 | RHI & FITS
Sheet 15 | Furniture
Sheet 16 | Communications
Sheet 17 | Seasonal Commissioning

## 1 Fire Management
Fire Management
Tasks | Description |  | Action | Dates | Complete | Comments
1 | Fire Risk Assessment for RRO |  |  |  | Yes
2 | Fit Fire Extinguishers |  |  |  | No
3 | Fit Fire Action Notices |  |  |  | Yes
4 | Appoint Fire Wardens |  |  |  | Yes
5 | Fit Evacuation Chair | 1No |  |  | Yes
6 | Fit Refuge Signs |  |  |  | Yes
7 | Premises information box |  |  |  | Yes
8 | Fire brigade visit |  |  |  | Yes
9 | Fire Safety Manual (inc plans) |  |  |  | Yes
10 | BU version of fire plans |  |  |  | Yes

## 2 Room Booking & Quemis
Room Booking & Quemis
Tasks | Description | Action | Dates | Complete | Comments
1 | Issue floor plans to KH/TF |  |  | Yes
2 | Agree Building Name |  |  | Yes
3 | Agree Room Numbering |  |  | Yes
4 | Set Up Room Booking System & Timetabling system |  |  | Yes
5 | Carry out Online Timetable test |  |  | No
6 | Room Layout Information Signs |  |  | Yes

## 3 Services Commissioning
Services Commissioning
Tasks | Description | Action | Dates | Complete | Comments
1.0 | Mechanical Commissioning
1.1 | Boilers |  |  | Yes
1.2 | AHUs & Air Balancing |  |  | Yes
1.3 | CHP |  |  | Yes
1.4 | GSHP |  |  | Yes
1.5 | BMS |  |  | No
1.6 | Rain Water Harvesting |  |  | No
1.7 | Hot and cold water systems |  |  | Yes
2.0 | Electrical Commissioning
2.1 | Power distribution |  |  | Yes
2.2 | Lighting |  |  | No
2.3 | Fire Alarm |  |  | Yes
2.4 | Intruder Alarm |  |  | Yes
2.5 | Disabled WC Alarms |  |  | Yes
2.6 | Refuge Intercom |  |  | Yes
2.7 | PV Panels |  |  | Yes
3.0 | Meters
3.1 | AMR
3.2 | Commission indvidual meters |  |  | Yes
3.3 | Meter Readings from first use |  |  | Yes
3.4 | Meter Readings at handover |  |  | Yes
4.0 | Drawing
4.1 | Schematic |  |  | Yes
5.0 | Lift Commissioning

## 4 Training
Training Record
Item | System/Description Demonstrated | Demonstrating Company | Date/Time | Client in attendance
1 | Electrical Distribution |  | Date:
| 1. Main Panel | MITIE | Time:
| 2. Distribution Boards | MITIE | Duration:
cv
2 | Lighting |  | Date:
| 1. Switching | MITIE | Time:
| 2. Automatic Switching | MITIE | Duration:
| 3. Emergency Testing | MITIE
3 | Small Power |  | Date:
| 1. Power Outlets | MITIE | Time:
| 2. Supplies to Plant/Controls | MITIE | Duration:
4 | Fire Alarm |  | Date:
| 1. Dealing with Alarm Activation | ADT | Time:
| 2. Auto Dialler | ADT | Duration:
| 3. Weekly Testing Procedure | ADT
| 4. Class Change | ADT | Date:
| 5. Warranties & Maintenance | ADT | Time:
Duration:
5 | Intruder Alarm Systems | CIA | Date:
| 1. Setting and Unsetting of the System | CIA | Time:
| 2. Setting of Management Codes | CIA | Duration:
| 3. Set-up of and Use of User Codes | CIA
| 4. What to do in the event of an Alarm | CIA | Date:
| 5. How to read the Log | CIA | Time:
| 6. Routine User Testing | CIA | Duration:
| 7. Warranties & Maintenance | CIA
6 | Door Access System |  | Date:
| 1. Operation of the System | CIA | Time:
| 2. Enrol a Card | CIA | Duration:
| 3. Cancel a Card | CIA | Date:
| 4. Management of Users | CIA | Time:
| 5. Warranties & Maintenance | CIA | Duration:
7 | Disabled Alarm |  | Date:
| 1.Operation of the System | CIA | Time:
| 2. Cancelling the alarm | CIA | Duration:
| 3. Warranties & Maintenance | CIA
8 | Induction Loop |  | Date:
| 1. Operation of System | GVMM | Time:
Duration:
9 | Telephone & Data Network |  | Date:
| 1. Location of Equipment Cab and Outlets | Lineartron | Time:
| 2. Location of Equipment WIFI outlets | Lineartron | Duration:
10 | Refuge Alarm |  | Date:
|  | CIA | Time:
Duration:
11 | Lightning Protection System |  | Date:
| 1. Location of Equipment |  | Time:
| 2. Warranties & Maintenance |  | Duration:
12 | Lighting Controls |  | Date:
| 1. Operation of system | MITIE | Time:
| 2. Warranties & Maintenance | MITIE | Duration:
13 | Lifts |  | Date:
| 1. Operation of system | Orona | Time:
| 2. Warranties & Maintenance | Orona | Duration:
14 | Mechanical Controls |  | Date
| Main Control Panel | Next Controls | Time:
| Room Control | Next Controls | Duration:
| Open Area Control | Next Controls
| Graphics and Alarming | Next Controls
| Metering | Next Controls
| Dashboard Display | Next Controls
15 | Mechanical
| Air Con | MITIE | Date
| Water Heating and Chilled Balancing | MITIE | Time
| Air Balancing Supply and Extract | MITIE | Duration
| Hot water Balance | MITIE
| Fire damper test | MITIE
| Set up Hot water temps | MITIE
16 | Ground Source Heat Pumps | Grund Holland | Date
Time
Duration
17 | PV Solar |  | Date
|  | Photon Energy | Time
Duration
18 | AV |  | Date
|  | GVMM | Time
Duration
19 | IT |  | Date
Time
Duration

## 5 Catering
Catering
Tasks | Description | Action by | Dates | Complete | Comments
1 | Catering Fit-Out |  |  | Yes
2.0 | Certification |  |  | Yes
2.1 | Electrical Testing |  |  | Yes
2.2 | Emergency Lighting |  |  | Yes
2.3 | Gas safety |  |  | Yes
2.4 | Water chlorination |  |  | Yes
2.5 | Fire suppression |  |  | Yes
2.6 | Handover Keys To BU |  |  | Yes
3.0 | Meter Readings |  |  | Yes
3.1 | Gas |  |  | Yes
3.2 | Electrical |  |  | Yes
3.3 | Water |  |  | Yes
Yes

## 6 O&Ms
Operation and Maintenance Manuals
Tasks | Description | Action | Dates | Complete | Comments
1 | Presentation of draft O&M Manuals |  |  | Yes
2 | Technical Adviser Review/approval |  |  | No
3 | Issue of O&M Manuals |  |  | Yes

## 7 AV IT
Audio Visual / IT
Tasks | Description | Action | Dates | Complete | Comments
1.0 | Communication Systems
1.1 | Install fibre infrastructure |  |  | Yes
1.2 | Install switch for lift commissioning |  |  | Yes
1.3 | Install switches and patching |  |  | Yes
1.4 | Install Internal Wifi APs |  |  | Yes
1.5 | Install External Wifi AP |  |  | Yes
1.6 | Fit UPS |  |  | Yes
2.0 | AV Systems
2.1 | Install Cabling |  |  | Yes
2.2 | Install Hardware |  |  | Yes
2.3 | Install Screens |  |  | Yes
2.4 | Install Whiteboards |  |  | Yes
2.5 | AV information sheet |  |  | Yes
3.0 | Room Scheduling Signs
3.1 | Install Crestron room panel feed |  |  | Yes
3.2 | Install Scheduling signs |  |  | Yes

## 8 Cleaning & Waste
Cleaning & Waste
Tasks | Description | Action by | Dates | Complete | Comments
1 | Interserve familiarisation |  |  | Yes
2 | Cleaning cupboard shelving |  |  | Yes
3 | Waste Bins for compound |  |  | No
4 | Internal recycling bins |  |  | No
5 | Sanitary bins |  |  | Yes
6 | Soap dispensers |  |  | Yes
7 | Toilet Roll Holders |  |  | Yes
8 | Soap |  |  | Yes
9 | Toilet Rolls |  |  | Yes
10 | BU cleaning to commence |  |  | Yes

## 9 Insurance
Insurance
Tasks | Description |  | Action | Dates | Complete | Comments
1 | Arrange Building Insurance |  |  |  | Yes
2 | Arrange Contents Insurance |  |  |  | Yes

## 10 Rates
Rates
Tasks | Description | Action | Dates | Complete | Comments
1 | Notify rates authority |  |  | Yes

## 11 Maint. Contracts
Maintenance Contracts
Tasks | Description | Action | Dates | Complete | Comments
1 | GSHP
2 | PV Panels
3 | AHUs
4 | Boilers
5 | CHP |  |  | Yes
6 | Pumps
7 | Lifts |  |  | Yes

## 12 Handover Docs
Handover Documents
Tasks | Description | Action | Dates | Complete | Comments
1.0 | Electrical Certification
1.1 | Electrical test |  |  | Yes
1.2 | Emergency Lighting |  |  | No
1.3 | Fire Alarm |  |  | Yes
1..4 | Intruder Alarm |  |  | No
1.5 | CCTV |  |  | No
1.6 | Disabled WC Alarms |  |  | No
1.7 | Disabled Refuge Intercom |  |  | Yes
1.8 | Lightning protection |  |  | Yes
2.0 | Mechanical Certification
2.1 | Gas |  |  | Yes
2.2 | Dry Risers |  |  | Yes
2.3 | Smoke vents |  |  | Yes
2.4 | Water chlorination |  |  | Yes
3.0 | Other Certification
3.1 | Lift test certification |  |  | Yes
3.2 | EPC |  |  | Yes
3.3 | DEC |  |  | Yes
3.4 | BREEAM Certificate |  |  | Yes
4.0 | Manuals
4.1 | Building O&M |  |  | Yes
4.2 | Electrical O&M |  |  | Yes
4.3 | Mechanical O&M |  |  | Yes
4.4 | Fire Manual |  |  | Yes
4.5 | Health & Safety File |  |  | Yes
4.6 | Building User Guide |  |  | Yes
5.0 | BIM
5.1 | Final 3D Revit Models for each discipline |  |  | Yes
5.2 | Federated Model for viewing in Navisworks |  |  | Yes
5.3 | Specialist sub-contractor design in 3D |  |  | Yes
Drawing Requirements See extract from BU Standards Below

## 13 Security
Security
Tasks | Description | Action | Dates | Complete | Comments
1 | Intruder Alarm interface with PH |  |  | Yes
2 | Fire alarm interface with PH |  |  | No
3 | CCTV interface with PH |  |  | Yes
4 | Handover of keys |  |  | No
5 | Lift cars interface with PH |  |  | No
6 | Salto |  |  | No

## 14 RHI & FITS
RHI & FITS
Tasks | Description | Action | Dates | Complete | Comments
1.0 | RHI Tasks
1.1 |  |  |  |  | To be arranged by Sustainability team
1.2
1.3
2.0 | FITS Tasks
2.1 |  |  |  |  | To be arranged by Sustainability team
2.2
2.3

## 15 Furniture
Furniture
Tasks | Description |  | Action | Dates | Complete | Comments
1.0 | Deliver and assemble |  |  |  | Yes

## 16 Communications
Communications
Tasks | Description | Action | Dates | Complete | Comments
1.0 |  | NM |  | Yes
Insert link to communications plan file folder

## 17 Seasonal Commissioning
Seasonal Commissioning
Tasks | Description | Action | Dates | Complete
Seasonal Commissioning 1
1.0 | Electrical Certification
1.1 | Electrical test |  |  | Yes
1.2 | Emergency Lighting |  |  | No
1.3 | Fire Alarm |  |  | No
1..4 | Intruder Alarm |  |  | No
1.5 | CCTV |  |  | No
1.6 | Disabled WC Alarms |  |  | No
1.7 | Disabled Refuge Intercom |  |  | No
1.8 | Lightning protection |  |  | Yes
2.0 | Mechanical Certification
2.1 | Gas |  |  | Yes
2.2 | Dry Risers |  |  | Yes
2.3 | Smoke vents |  |  | Yes
2.4 | Water chlorination |  |  | Yes
3.0 | Other Certification
3.1 | Lift test certification |  |  | Yes
3.2 | EPC |  |  | Yes
3.3 | DEC |  |  | Yes
Seasonal Commissioning 2

## 18 Moves and Occupation
TASKS
PLANNING
Agree high level objectives and scope for the move
Include team names and locations - From and To
In and out of scope, ie - furniture, PCs, equipment, supply of crates etc. Does existing space need to be cleared of redundant items or will that be picked up by a separate project?
Confirm move budget and how this is broken down
Produce high level programme for the move
Identify the key dates for completion / BU fit out / move / occupation / building go-live. Ensure sufficient contingency
Phased move or continuous / gradual flow?
Identify all stakeholders and establish roles and responsibilities for the move
End user team reps, end user dept reps, move contractor TBA, IT (contractor)?, any specialist engineers/movers required? BU project manager, Estates FM.
Room audits / room data sheets
Existing and proposed. Identify what is moving / staying / disposal and identify any special arrangements required eg - specialist moves
Document detailed move requirements
Meet all end user group reps to discuss and agree move requirements.
Clarify criteria for acceptance of the space and any operational issues/requirements around proposed move dates.
What are the absolute drop dead dates?
Identify any new staff joining during the move period
Are there any interim storage requirements during the move period?
Are there any interim hot desking requirements during the move period?
Are there any DSE requirements for individual staff? Eg height adjustable desks, DSE chairs etc
Can all staff pack themselves?
Particular IT setup requirements eg - which side mouse goes etc
Review floor plans, identify any issues and confirm desk allocations where staff have fixed desks.
Review requirements for crates - use existing / purchase / hire?
Produce detailed move plans and schedules
Produce detailed move schedule linking to FFE plans.
All plans to show FFE with unique item codes for identification, linked to room data sheets. Room data sheets to identify categories 1 - 4. Staff names to be linked to desk numbers where there is fixed desking.
To be signed off by end users prior to ITT issue.
Also include any requirements for disposal of unwanted items.
Consider arrangements / procurement for moves of specialist equipment.
Consider training requirements on any new equipment, building procedures etc
Consider arrangements for printer moves
Feedback any issues identified to PM eg - furniture spec incorrect etc
Identify risk areas and make contingency plans.
Construction delays
Access problems
IT requirements
Furniture delivery issues
Security issues - items left unattended and accessible during move
Removal company issues/failure
Bad weather
Produce a risk assessment to include all high risk, valuable / fragile items or hazardous goods requiring special handling
Communication
Establish regular meetings with end user reps to update on progress and review queries / outstanding issues
Ensure end users are planning to dispose of all unwanted items and audit / cull file storage prior to the move.
PROCUREMENT OF SERVICES
Prepare detailed specification / scope of work for each service required -
IE - furniture and equipment moves / IT disconnections and re-connections / specialist de-commissioning & re-commissioning
Movers must be certified to BS8522 (commercial). Clarify insurance cover required for the move. Emergency procedures / first aiders / accident reporting procedures
Conduct tender process as required according to proposed value of services required
Review tenders returns and appoint contractors / suppliers
Arrange and conduct pre move planning meetings with move contractor
Contractor to produce daily move plan and RAMS for review and approval
BUILDING HANDOVER AND PRE-MOVE CHECKS
Confirm all building infrastructure operational prior to move, eg :
Lifts
Toilets
HVAC
Catering
Power & data
Access control
Kitchen facilities / drinking water
Waste management and cleaning
Cycle storage and showers
Building signage
Issue move guide for staff (to include numbered plans to show desk locations, building facilities / procedures / access details etc . Clarify labelling strategy).
Consider pre-move building tours and training sessions where required (new equipment, fire safety etc)
All crates and low tack labels delivered to end users for packing. Check and document how many allocated to each area so that they are traceable (crate ID numbers?).
All new furniture installed correctly prior to move as per signed off floor plans
All staff are packed and ready to move
Arrange handover of all keys and updates to access control cards / new cards where required
All crates and furniture labelled as per FFE plans
New desks physically labelled with numbers to assist porters
Move contractor & IT contractor ready and building access arranged
Lift protection arranged
Callout procedures arranged eg - lift engineers, electricians etc
Procedures for reporting of issues arranged
Any mid move and post move progress meetings arranged
Arrangements for mail re-routing are in place.
Any interim hot desking / storage facilities are ready
General comms issued
Agree a holding area for unlabelled or problem items
Agree responsibilities for any staff assisting with directing the move at both locations.
Building / move security procedures clarified and in place
MOVE
Make a list of problems as they arise (produce template for capturing these and establish reporting procedure)
Check no items left behind in existing areas
Check readiness of new areas prior to occupation
OCCUPATION
Troubleshooting - Move manager to maintain presence in building to pick up on problems as they are reported
Confirm building contractor and BU IT available or on call to resolve any urgent issues
Add to problem log as items are reported
Ensure users test all aspects of their operation - eg IT equipment used in infrequent tasks may only become apparent at a much later date if not tested.
POST-OCCUPATION
Remove all furniture labels promptly
collect all crates and off-hire
Resolve all items on problem log
Obtain post occupation feedback from building users

## 19 SL Programme
Meetings (steering/oversite/ whole stakeholder group/detail), key build programme dates, add stakeholders to activities
Group Name | Stakeholders | Attendees | Frequency of meetings | Date | Agenda items
Soft Landings Oversight Group |  |  |  |  | Soft Landings oversight, key issue resolution, coordination with cap dev programme etc
Soft Landings Stakeholder Group |  |  |  |  | Intro's, general project update, programme update, soft landings procees and updates from groups
Kier Soft Landings Group |  |  |  |  | Programme, supply chain coordination, training, O&M's, User Guide, Aftercare arrangements
Fire Management Group |  |  |  |  | Programme update, FRA, fire fighting equipment, action notices, wardens, evac chairs, refuges, info box, plans etc
Room Bookings and Quemis Group |  |  |  |  | Timetabling, room booking system, programme, tests, signage
Services Commissioning Group |  |  |  |  | Programme, supply chain coordination, mech, elec, meter, lifts
Training and Demonstrations Group |  |  |  |  | Training matrix, training methodolgy, programme, supply chain coordination
Catering Group |  |  |  |  | Certification, testing, meters, resourcing, programme, changes
O&M's / Handover Docs / Building user guide group |  |  |  |  | Formating, supply chain coordination, programme, approvals
AV/IT Group |  |  |  |  | Programme, provider, costs, specification, re-use (timetabling)
Cleaning and Waste Group |  |  |  |  | Review plans etc, confirm requirements, orders, timings, installations, changes to SLA's
Insurance and Rates |  |  |  |  | PM to notify handover date. No meetings envisaged
Maintenance Contracts & Soft FM Requirements Group |  |  |  |  | All maintenance, soft FM requirements including security, programme, SLA changes, maintenance contract changes
Sustainability Group RHI & FITS |  |  |  |  | RHI / FITS / Meters etc
Furniture Group |  |  |  |  | Design, cost, engagement, approvals, programme
Communications Group |  |  |  |  | Development of Plan, update on BGB, actions in the period, feedback
Moves and Occupation Group |  |  |  |  | Review membership, programme, appointments, communication, POE
Insert high level soft landings programme below

## 20 Commissioning roles & resps
Commissioning Responsibility Matrix
To be adjusted to suit specific project requirements
Organisation | Roles | Representative | Description of service | Cost | Oversight group member
Client | Soft Landings Champion |  | Oversight of the Soft Landings for the project
| Commisioning Manager |  | All client side commissioning manager activities as set out in the construction consultant contract
| Commissioning Manager's Engineers |  | Specialist engineer appointed by Construction Consultant to oversee technical aspects of commissioning
| NEC Supervisor |  | NEC Supervisor duties, test witnessing etc
| BU Project Manager |  | Oversight of the commissioning process and outcomes
| BU Maintenance/Soft FM Team |  | Input into process, organising all maintenance and building servicing requirements and feedback
| BU Sustainability Team |  | Input into process, obtaining meter readings and organising RHI/FITS, utilities on going contracts and efficiencies and feedback
| End User |  | Specialist furniture, equipment, RFID, installation and testing
Contractor | Main Contractor |  | Installation, testing and commissioning of all building services and facilites, including programme management to ensure adequate time provided
| M&E Sub Contractor |  | M&E Subcontractor
| M&E Sub Contractor Specialist Commissioning Managers |  | Specialist commissioning engineers to balance all services to achieve design intent
| M&E Sub Contractor - Controls Specialist |  | Specialist controls engineers to feed into commissioning and ensure integration into BU's control systems
| Design Engineers |  | Consultant engineer oversight